## LEGEND & SUMMARY
PMO 01 - Project Plan Review & Feasibility Validation Agent ¦ Mock Dataset
Input for an agent that checks a Project Plan for completeness vs the PMO template, detects timeline/resource/dependency feasibility risks, and benchmarks against similar historical projects. Shared masters (members, projects) are identical to the PMO 02 file. NOTE: DS03 is a representative snapshot; a plan's Team_size is the full planned headcount, so not every team member appears in the current allocation window.
Sheet | Grain (1 row =) | Field | Type | Example | Description
DS01_Project_Plan | 1 task / milestone in a plan under review | Project_ID | String | PRJ-002 | Project the plan belongs to (FK -> Project_Master).
|  | Project_name | String | Energent AI | Project name.
|  | Task_ID | String | TASK-E04 | Unique task id within the plan.
|  | Task_name | String | Model training service | Task description.
|  | Assignee_id | String | EMP-003 | Member assigned (FK -> Member_Master).
|  | Start_date | Date | 2026-06-01 | Task start (YYYY-MM-DD).
|  | End_date | Date | 2026-08-21 | Task end; must be >= start.
|  | Effort_days | Float | 110.0 | Estimated effort (man-days); sums to plan effort.
|  | Percent_complete | Float | 0.40 | Completion 0.0-1.0 at snapshot.
|  | Status | Enum | In Progress | Not Started/In Progress/Completed/Blocked/Delayed.
|  | Milestone_flag | Bool | TRUE | TRUE if task is a milestone.
|  | Dependencies | String | TASK-E08 | CSV of prerequisite task ids (may form a cycle!).
|  | Phase | String | Development | Discovery/Design/Development/Testing/Deployment.
|  | Risk_note | String | Key person risk | Task-level risk note.
DS02_PMO_Standard_Template | 1 required component of the PMO template | Template_ID | String | TPL-2026-v3 | Template version id.
|  | Template_name | String | Standard Project Plan Template | Template name.
|  | Version | String | 3.0 | Version.
|  | Effective_date | Date | 2026-01-01 | Effective date.
|  | Component_ID | String | COMP-007 | Component id.
|  | Section_code | String | S07 | Section code S01-S08.
|  | Component_name | String | Risk_RAID | Required component name.
|  | Required | Bool | TRUE | TRUE = mandatory in every plan.
|  | Validation_rule | String | >=1 risk entry | Validity rule.
|  | Weight | Float | 0.16 | Scoring weight (all components sum to 1.0).
DS03_Resource_Allocation | 1 member x project allocation (current snapshot) | Member_ID | String | EMP-004 | Member (FK -> Member_Master).
|  | Project_ID | String | PRJ-001 | Project (FK -> Project_Master).
|  | Role | Enum | BE | Role code on this allocation.
|  | Allocation_pct | Float | 0.80 | Share of the member's standard week.
|  | Start_date | Date | 2026-06-29 | Allocation start.
|  | End_date | Date | 2026-08-07 | Allocation end.
|  | Busy_rate | Float | 1.25 | Sum of the member's allocation across projects.
DS04_Velocity_History | 1 sprint of a completed project | Project_ID | String | PRJ-H-103 | Historical project (FK).
|  | Project_type | String | AI/ML Platform | Project type.
|  | Sprint_no | Int | 3 | Sprint number.
|  | Sprint_duration_days | Int | 14 | Sprint length.
|  | Planned_points | Float | 40.0 | Planned story points.
|  | Completed_points | Float | 37.2 | Completed story points.
|  | Velocity_ratio | Float | 0.93 | Completed / planned.
|  | Team_size | Int | 9 | Team size that sprint.
|  | Outcome | Enum | Completed | Sprint outcome.
DS05_Historical_Projects | 1 completed project (benchmark) | Historical_project_id | String | PRJ-H-101 | Historical project id.
|  | Project_type | String | Software/Migration | Type (filter for similar benchmark).
|  | Team_size | Int | 8 | Team size.
|  | Duration_days | Int | 240 | Actual duration.
|  | Planned_duration_days | Int | 225 | Planned duration.
|  | Total_effort_days | Float | 180.0 | Actual effort (man-days).
|  | Total_budget_scaled | Float | 8.6 | Scaled budget (1.0 = baseline).
|  | Avg_velocity_ratio | Float | 0.92 | Avg velocity ratio.
|  | Risk_count | Int | 5 | Risks raised.
|  | Key_risks | String | Cutover risk | Generalized key risks.
|  | PMO_standard_ver | String | 2.1 | PMO template version used.
|  | Final_outcome | Enum | On Time | On Time/Delayed/Cancelled/Early.
|  | Is_outlier | Bool | FALSE | TRUE = exclude from benchmarking (e.g. tiny POC).
DS06_Plan_Section_Check [ADDED] | 1 template component checked against a plan | Check_ID | String | CHK-015 | Check id.
|  | Plan_ID | String | PLAN-002 | Plan reviewed.
|  | Component_ID | String | COMP-007 | Template component (NULL if custom).
|  | Custom_name | String | EVM_Cost_Tracking | Name when status = Custom.
|  | Status | Enum | Missing | Complete/Weak/Missing/Custom.
|  | Note | String | Risk Register absent | Why weak/missing/custom.
DS07_Project_Plan_Summary [ADDED] | 1 plan under review (header metrics) | Plan_ID | String | PLAN-002 | Plan id.
|  | Project_ID | String | PRJ-002 | Project.
|  | Project_name | String | Energent AI | Project name.
|  | Plan_set | String | To_Review | Review queue.
|  | Effort_MD | Float | 426 | Total effort (man-days).
|  | Duration_months | Float | 9 | Planned duration.
|  | Velocity_MD_month | Float | 47.3 | Effort / duration.
|  | Team_size | Int | 10 | Planned peak team.
|  | Risk_count | Int | 0 | Risks registered (0 = missing register).
|  | Top_risk_score | Float |  | Highest risk score.
|  | THI_pct | Float | 9 | Tech-health index %.
|  | Peak_role_busy_rate_pct | Float | 135 | Peak role demand vs capacity.
|  | On_time_history_pct | Float | 90 | PM on-time history.
|  | Feasibility_status | String | Not feasible (Red) | Reviewer verdict.
DS08_Role_Capacity [ADDED] | 1 role's current capacity | Capacity_ID | String | CAP-08 | Capacity id.
|  | Role | String | Security Engineer | Role.
|  | Headcount | Int | 2 | People in role.
|  | Capacity_MD_month | Float | 44 | Capacity man-days/month.
|  | Busy_rate_pct | Float | 95 | Current busy %.
|  | Available_MD_month | Float | 2 | Spare man-days/month.
|  | Note | String | Bottleneck | Capacity note.
REF_Member_Master [SHARED/REF] | 1 member (shared with Problem 2) | Member_ID | String | EMP-003 | Member id.
|  | Full_name | String | Le Van Cuong | Name.
|  | Role_title | String | ML Engineer | Title.
|  | Department | String | AI/ML | Department.
|  | Employment | Enum | FT | FT/PT.
|  | Std_hours_week | Float | 40 | Standard hours/week.
REF_Project_Master [SHARED/REF] | 1 project (shared with Problem 2) | Project_ID | String | PRJ-002 | Project id.
|  | Project_name | String | Energent AI | Name.
|  | Project_type | String | AI/ML Platform | Type.
|  | Status | Enum | Active | Lifecycle status.
|  | Is_historical | Bool | FALSE | TRUE for completed/benchmark.
REF_KPI_Norms [SHARED/REF] | 1 RAG metric threshold (SETA-08-SOP-001) | Norm_ID | String | N07 | Norm id.
|  | Metric | String | On-time Delivery | Metric.
|  | Green/Yellow/Red | String | >=90% / ... | RAG thresholds.
Answer_Key [ANSWER KEY] | 1 finding the agent should detect (Problem 1) | Finding_ID | String | F-01 | Finding id.
|  | Entity_id | String | PLAN-002 | Member/plan/benchmark.
|  | Issue_type | String | Missing_section | Category.
|  | Expected_detection | String | Risk Register missing | What to detect.
|  | Severity | String | High | Severity.

## DS01_Project_Plan
Project_ID | Project_name | Task_ID | Task_name | Assignee_id | Start_date | End_date | Effort_days | Percent_complete | Status | Milestone_flag | Dependencies | Phase | Risk_note
PRJ-001 | Project Orion (Core Banking) | TASK-O01 | Requirements & scope workshop | EMP-008 | 2026-05-19 | 2026-05-29 | 8 | 1 | Completed | FALSE |  | Discovery
PRJ-001 | Project Orion (Core Banking) | TASK-O02 | As-is core banking assessment | EMP-004 | 2026-05-19 | 2026-06-05 | 12 | 1 | Completed | TRUE | TASK-O01 | Discovery | Legacy COBOL knowledge scarce
PRJ-001 | Project Orion (Core Banking) | TASK-O03 | Target architecture design | EMP-004 | 2026-06-08 | 2026-06-26 | 15 | 0.8 | In Progress | FALSE | TASK-O02 | Design
PRJ-001 | Project Orion (Core Banking) | TASK-O04 | Security & PCI design | EMP-006 | 2026-06-15 | 2026-07-03 | 12 | 0.6 | In Progress | FALSE | TASK-O02 | Design | PCI audit dependency
PRJ-001 | Project Orion (Core Banking) | TASK-O05 | Account service migration | EMP-001 | 2026-07-06 | 2026-08-28 | 30 | 0.2 | In Progress | FALSE | TASK-O03 | Development
PRJ-001 | Project Orion (Core Banking) | TASK-O06 | Transaction engine build | EMP-001 | 2026-07-20 | 2026-09-18 | 35 | 0.1 | Not Started | TRUE | TASK-O03,TASK-O04 | Development
PRJ-001 | Project Orion (Core Banking) | TASK-O07 | CI/CD & infra automation | EMP-005 | 2026-07-06 | 2026-08-14 | 18 | 0.3 | In Progress | FALSE | TASK-O03 | Development
PRJ-001 | Project Orion (Core Banking) | TASK-O08 | SIT — system integration test | EMP-010 | 2026-09-21 | 2026-10-16 | 20 | 0 | Not Started | FALSE | TASK-O05,TASK-O06 | Testing
PRJ-001 | Project Orion (Core Banking) | TASK-O09 | Security penetration test | EMP-006 | 2026-10-05 | 2026-10-23 | 10 | 0 | Not Started | FALSE | TASK-O06,TASK-O04 | Testing
PRJ-001 | Project Orion (Core Banking) | TASK-O10 | Cutover & go-live | EMP-005 | 2026-11-02 | 2026-11-20 | 8 | 0 | Not Started | TRUE | TASK-O08,TASK-O09 | Deployment | Rollback window tight
PRJ-002 | Energent AI (Data Platform) | TASK-E01 | Data sources & scope mapping | EMP-008 | 2026-04-06 | 2026-04-17 | 12 | 1 | Completed | FALSE |  | Discovery
PRJ-002 | Energent AI (Data Platform) | TASK-E02 | Feature store & pipeline design | EMP-002 | 2026-04-20 | 2026-05-15 | 30 | 0.9 | In Progress | TRUE | TASK-E01 | Design
PRJ-002 | Energent AI (Data Platform) | TASK-E03 | Ingestion pipeline build | EMP-002 | 2026-05-18 | 2026-07-10 | 70 | 0.5 | In Progress | FALSE | TASK-E02 | Development
PRJ-002 | Energent AI (Data Platform) | TASK-E04 | Model training service | EMP-003 | 2026-06-01 | 2026-08-21 | 110 | 0.4 | In Progress | TRUE | TASK-E02 | Development | Single ML engineer — key person risk
PRJ-002 | Energent AI (Data Platform) | TASK-E05 | Frontend dashboard | EMP-009 | 2026-07-13 | 2026-09-04 | 55 | 0 | Not Started | FALSE | TASK-E03 | Development
PRJ-002 | Energent AI (Data Platform) | TASK-E06 | Model validation testing | EMP-010 | 2026-06-15 | 2026-08-30 | 35 | 0 | Not Started | FALSE | TASK-E04 | Testing | Starts before model service completes — order risk
PRJ-002 | Energent AI (Data Platform) | TASK-E07 | Integration & release | EMP-005 | 2026-09-07 | 2026-09-25 | 28 | 0 | Not Started | TRUE | TASK-E08 | Deployment | Cyclic dependency with E08
PRJ-002 | Energent AI (Data Platform) | TASK-E08 | End-to-end acceptance test | EMP-010 | 2026-09-28 | 2026-10-16 | 30 | 0 | Not Started | FALSE | TASK-E07 | Testing | Cyclic dependency with E07
PRJ-002 | Energent AI (Data Platform) | TASK-E09 | MLOps monitoring setup | EMP-005 | 2026-08-03 | 2026-08-28 | 30 | 0 | Not Started | FALSE | TASK-E04 | Development
PRJ-002 | Energent AI (Data Platform) | TASK-E10 | Production rollout | EMP-005 | 2026-10-19 | 2026-11-06 | 26 | 0 | Not Started | TRUE | TASK-E07,TASK-E08 | Deployment
PRJ-101 | Project Apollo | TASK-101-01 | Discovery work package 1 | EMP-106 | 2026-04-05 | 2026-09-12 | 26.2 | 0.54 | Completed | FALSE |  | Discovery
PRJ-101 | Project Apollo | TASK-101-02 | Design work package 2 | EMP-105 | 2026-04-05 | 2026-09-12 | 26.3 | 0 | In Progress | TRUE | TASK-101-01 | Design
PRJ-101 | Project Apollo | TASK-101-03 | Development work package 3 | EMP-107 | 2026-04-05 | 2026-09-12 | 26.2 | 0.29 | In Progress | FALSE | TASK-101-02 | Development
PRJ-101 | Project Apollo | TASK-101-04 | Development work package 4 | EMP-103 | 2026-04-05 | 2026-09-12 | 26.3 | 0.35 | In Progress | FALSE | TASK-101-03 | Development
PRJ-101 | Project Apollo | TASK-101-05 | Testing work package 5 | EMP-117 | 2026-04-05 | 2026-09-12 | 26.2 | 0.15 | In Progress | FALSE | TASK-101-04 | Testing
PRJ-101 | Project Apollo | TASK-101-06 | Deployment work package 6 | EMP-111 | 2026-04-05 | 2026-09-12 | 26.3 | 0.07 | Completed | TRUE | TASK-101-05 | Deployment
PRJ-102 | Project Vega | TASK-102-01 | Discovery work package 1 | EMP-107 | 2026-04-11 | 2026-11-11 | 30 | 0.35 | In Progress | FALSE |  | Discovery
PRJ-102 | Project Vega | TASK-102-02 | Design work package 2 | EMP-103 | 2026-04-11 | 2026-11-11 | 30 | 0.07 | Not Started | TRUE | TASK-102-01 | Design
PRJ-102 | Project Vega | TASK-102-03 | Development work package 3 | EMP-111 | 2026-04-11 | 2026-11-11 | 30 | 0.4 | Completed | FALSE | TASK-102-02 | Development
PRJ-102 | Project Vega | TASK-102-04 | Development work package 4 | EMP-117 | 2026-04-11 | 2026-11-11 | 30 | 0.41 | In Progress | FALSE | TASK-102-03 | Development
PRJ-102 | Project Vega | TASK-102-05 | Testing work package 5 | EMP-105 | 2026-04-11 | 2026-11-11 | 30 | 0.31 | Not Started | FALSE | TASK-102-04 | Testing
PRJ-102 | Project Vega | TASK-102-06 | Deployment work package 6 | EMP-116 | 2026-04-11 | 2026-11-11 | 30 | 0.53 | Completed | TRUE | TASK-102-05 | Deployment
PRJ-103 | Project Lyra | TASK-103-01 | Discovery work package 1 | EMP-105 | 2026-03-08 | 2026-10-16 | 30 | 0.41 | Not Started | FALSE |  | Discovery
PRJ-103 | Project Lyra | TASK-103-02 | Design work package 2 | EMP-118 | 2026-03-08 | 2026-10-16 | 30 | 0.27 | Not Started | TRUE | TASK-103-01 | Design
PRJ-103 | Project Lyra | TASK-103-03 | Development work package 3 | EMP-109 | 2026-03-08 | 2026-10-16 | 30 | 0.19 | In Progress | FALSE | TASK-103-02 | Development
PRJ-103 | Project Lyra | TASK-103-04 | Development work package 4 | EMP-108 | 2026-03-08 | 2026-10-16 | 30 | 0.42 | In Progress | FALSE | TASK-103-03 | Development
PRJ-103 | Project Lyra | TASK-103-05 | Testing work package 5 | EMP-113 | 2026-03-08 | 2026-10-16 | 30 | 0.3 | Not Started | FALSE | TASK-103-04 | Testing
PRJ-103 | Project Lyra | TASK-103-06 | Deployment work package 6 | EMP-107 | 2026-03-08 | 2026-10-16 | 30 | 0.35 | Completed | TRUE | TASK-103-05 | Deployment
PRJ-104 | Project Draco | TASK-104-01 | Discovery work package 1 | EMP-107 | 2026-04-27 | 2026-12-06 | 23.3 | 0.36 | Completed | FALSE |  | Discovery
PRJ-104 | Project Draco | TASK-104-02 | Design work package 2 | EMP-105 | 2026-04-27 | 2026-12-06 | 23.3 | 0.02 | In Progress | TRUE | TASK-104-01 | Design
PRJ-104 | Project Draco | TASK-104-03 | Development work package 3 | EMP-117 | 2026-04-27 | 2026-12-06 | 23.4 | 0.29 | In Progress | FALSE | TASK-104-02 | Development
PRJ-104 | Project Draco | TASK-104-04 | Development work package 4 | EMP-111 | 2026-04-27 | 2026-12-06 | 23.3 | 0.31 | In Progress | FALSE | TASK-104-03 | Development
PRJ-104 | Project Draco | TASK-104-05 | Testing work package 5 | EMP-116 | 2026-04-27 | 2026-12-06 | 23.4 | 0.52 | Completed | FALSE | TASK-104-04 | Testing
PRJ-104 | Project Draco | TASK-104-06 | Deployment work package 6 | EMP-104 | 2026-04-27 | 2026-12-06 | 23.3 | 0.43 | Completed | TRUE | TASK-104-05 | Deployment

## DS02_PMO_Standard_Template
Template_ID | Template_name | Version | Effective_date | Component_ID | Section_code | Component_name | Required | Validation_rule | Weight
TPL-2026-v3 | Standard Project Plan Template | 3.0 | 2026-01-01 | COMP-001 | S01 | Scope | TRUE | Scope statement + in/out-of-scope list | 0.12
TPL-2026-v3 | Standard Project Plan Template | 3.0 | 2026-01-01 | COMP-002 | S02 | Objectives | TRUE | ≥1 measurable objective (SMART) | 0.1
TPL-2026-v3 | Standard Project Plan Template | 3.0 | 2026-01-01 | COMP-003 | S03 | Milestones | TRUE | All milestones have target dates | 0.12
TPL-2026-v3 | Standard Project Plan Template | 3.0 | 2026-01-01 | COMP-004 | S04 | WBS_Effort | TRUE | Every WBS task has effort estimate | 0.13
TPL-2026-v3 | Standard Project Plan Template | 3.0 | 2026-01-01 | COMP-005 | S05 | Resource_Plan | TRUE | Role × allocation table present | 0.13
TPL-2026-v3 | Standard Project Plan Template | 3.0 | 2026-01-01 | COMP-006 | S06 | Dependencies | TRUE | Dependency graph is acyclic | 0.12
TPL-2026-v3 | Standard Project Plan Template | 3.0 | 2026-01-01 | COMP-007 | S07 | Risk_RAID | TRUE | ≥1 risk entry with severity + owner | 0.16
TPL-2026-v3 | Standard Project Plan Template | 3.0 | 2026-01-01 | COMP-008 | S08 | Acceptance_Criteria | TRUE | Each deliverable has measurable AC | 0.12

## DS03_Resource_Allocation
Member_ID | Project_ID | Role | Allocation_pct | Start_date | End_date | Busy_rate
EMP-001 | PRJ-001 | BE | 0.6 | 2026-06-29 | 2026-08-07 | 1.15
EMP-001 | PRJ-003 | BE | 0.55 | 2026-06-29 | 2026-08-07 | 1.15
EMP-002 | PRJ-002 | DE | 0.9 | 2026-06-29 | 2026-08-07 | 0.9
EMP-003 | PRJ-002 | ML | 1 | 2026-06-29 | 2026-08-07 | 1
EMP-004 | PRJ-001 | BE | 0.8 | 2026-06-29 | 2026-08-07 | 1.25
EMP-004 | PRJ-002 | BE | 0.45 | 2026-06-29 | 2026-08-07 | 1.25
EMP-005 | PRJ-001 | DevOps | 0.3 | 2026-06-29 | 2026-08-07 | 0.6
EMP-005 | PRJ-002 | DevOps | 0.3 | 2026-06-29 | 2026-08-07 | 0.6
EMP-006 | PRJ-001 | Sec | 0.95 | 2026-06-29 | 2026-08-07 | 0.95
EMP-007 | PRJ-002 | Design | 0.8 | 2026-06-29 | 2026-08-07 | 0.8
EMP-008 | PRJ-002 | BA | 0.5 | 2026-06-29 | 2026-08-07 | 0.5
EMP-009 | PRJ-002 | FE | 0.8 | 2026-07-13 | 2026-08-07 | 0.8
EMP-010 | PRJ-001 | QA | 0.6 | 2026-06-29 | 2026-08-07 | 1.1
EMP-010 | PRJ-002 | QA | 0.5 | 2026-06-29 | 2026-08-07 | 1.1
EMP-103 | PRJ-103 | BE | 0.86 | 2026-06-29 | 2026-08-07 | 0.86
EMP-104 | PRJ-102 | BA | 0.85 | 2026-06-29 | 2026-08-07 | 0.85
EMP-105 | PRJ-106 | DevOps | 0.86 | 2026-06-29 | 2026-08-07 | 0.86
EMP-106 | PRJ-103 | FE | 1.01 | 2026-06-29 | 2026-08-07 | 1.01
EMP-107 | PRJ-104 | DE | 0.45 | 2026-06-29 | 2026-08-07 | 0.95
EMP-107 | PRJ-102 | DE | 0.5 | 2026-06-29 | 2026-08-07 | 0.95
EMP-108 | PRJ-102 | FE | 0.53 | 2026-06-29 | 2026-08-07 | 0.92
EMP-108 | PRJ-103 | FE | 0.39 | 2026-06-29 | 2026-08-07 | 0.92
EMP-109 | PRJ-108 | DevOps | 0.96 | 2026-06-29 | 2026-08-07 | 0.96
EMP-110 | PRJ-101 | FE | 0.56 | 2026-06-29 | 2026-08-07 | 0.98
EMP-110 | PRJ-105 | FE | 0.42 | 2026-06-29 | 2026-08-07 | 0.98
EMP-111 | PRJ-105 | BA | 1.04 | 2026-06-29 | 2026-08-07 | 1.04
EMP-112 | PRJ-105 | BA | 0.44 | 2026-06-29 | 2026-08-07 | 1.04
EMP-112 | PRJ-102 | BA | 0.6 | 2026-06-29 | 2026-08-07 | 1.04
EMP-113 | PRJ-106 | BE | 0.86 | 2026-06-29 | 2026-08-07 | 0.86
EMP-114 | PRJ-102 | Design | 0.43 | 2026-06-29 | 2026-08-07 | 0.91
EMP-114 | PRJ-108 | Design | 0.48 | 2026-06-29 | 2026-08-07 | 0.91
EMP-115 | PRJ-102 | Design | 0.6 | 2026-06-29 | 2026-08-07 | 0.92
EMP-115 | PRJ-105 | Design | 0.32 | 2026-06-29 | 2026-08-07 | 0.92
EMP-116 | PRJ-105 | QA | 0.49 | 2026-06-29 | 2026-08-07 | 0.98
EMP-116 | PRJ-104 | QA | 0.49 | 2026-06-29 | 2026-08-07 | 0.98
EMP-117 | PRJ-102 | ML | 0.49 | 2026-06-29 | 2026-08-07 | 1.04
EMP-117 | PRJ-106 | ML | 0.55 | 2026-06-29 | 2026-08-07 | 1.04
EMP-118 | PRJ-101 | Design | 0.48 | 2026-06-29 | 2026-08-07 | 1.09
EMP-118 | PRJ-105 | Design | 0.61 | 2026-06-29 | 2026-08-07 | 1.09

## DS04_Velocity_History
Project_ID | Project_type | Sprint_no | Sprint_duration_days | Planned_points | Completed_points | Velocity_ratio | Team_size | Outcome
PRJ-H-101 | Software/Migration | 1 | 14 | 40 | 34 | 0.85 | 8 | Completed
PRJ-H-101 | Software/Migration | 2 | 14 | 40 | 36 | 0.9 | 8 | Completed
PRJ-H-101 | Software/Migration | 3 | 14 | 40 | 38 | 0.95 | 8 | Completed
PRJ-H-101 | Software/Migration | 4 | 14 | 40 | 38 | 0.95 | 8 | Completed
PRJ-H-101 | Software/Migration | 5 | 14 | 40 | 38 | 0.95 | 8 | Completed
PRJ-H-102 | Software/Migration | 1 | 14 | 40 | 36.8 | 0.92 | 7 | Completed
PRJ-H-102 | Software/Migration | 2 | 14 | 40 | 38 | 0.95 | 7 | Completed
PRJ-H-102 | Software/Migration | 3 | 14 | 40 | 38.4 | 0.96 | 7 | Completed
PRJ-H-102 | Software/Migration | 4 | 14 | 40 | 38 | 0.95 | 7 | Completed
PRJ-H-102 | Software/Migration | 5 | 14 | 40 | 38.8 | 0.97 | 7 | Completed
PRJ-H-103 | AI/ML Platform | 1 | 14 | 40 | 32.8 | 0.82 | 9 | Completed
PRJ-H-103 | AI/ML Platform | 2 | 14 | 40 | 35.2 | 0.88 | 9 | Completed
PRJ-H-103 | AI/ML Platform | 3 | 14 | 40 | 36.8 | 0.92 | 9 | Completed
PRJ-H-103 | AI/ML Platform | 4 | 14 | 40 | 37.2 | 0.93 | 9 | Completed
PRJ-H-103 | AI/ML Platform | 5 | 14 | 40 | 38 | 0.95 | 9 | Completed
PRJ-H-104 | AI/ML Platform | 1 | 14 | 40 | 35.2 | 0.88 | 8 | Completed
PRJ-H-104 | AI/ML Platform | 2 | 14 | 40 | 36.8 | 0.92 | 8 | Completed
PRJ-H-104 | AI/ML Platform | 3 | 14 | 40 | 37.6 | 0.94 | 8 | Completed
PRJ-H-104 | AI/ML Platform | 4 | 14 | 40 | 38 | 0.95 | 8 | Completed
PRJ-H-104 | AI/ML Platform | 5 | 14 | 40 | 38.4 | 0.96 | 8 | Completed
PRJ-H-105 | Software | 1 | 14 | 40 | 36 | 0.9 | 5 | Completed
PRJ-H-105 | Software | 2 | 14 | 40 | 37.2 | 0.93 | 5 | Completed
PRJ-H-105 | Software | 3 | 14 | 40 | 38 | 0.95 | 5 | Completed
PRJ-H-105 | Software | 4 | 14 | 40 | 38.4 | 0.96 | 5 | Completed
PRJ-H-105 | Software | 5 | 14 | 40 | 38.4 | 0.96 | 5 | Completed
PRJ-H-199 | AI/ML Platform | 1 | 7 | 40 | 40 | 1 | 2 | Completed
PRJ-H-201 | Software/Migration | 1 | 14 | 40 | 39.8 | 0.995 | 7 | Completed
PRJ-H-201 | Software/Migration | 2 | 14 | 40 | 38.4 | 0.96 | 7 | Completed
PRJ-H-201 | Software/Migration | 3 | 14 | 40 | 37 | 0.925 | 7 | Completed
PRJ-H-201 | Software/Migration | 4 | 14 | 40 | 40.1 | 1.0025 | 7 | Completed
PRJ-H-201 | Software/Migration | 5 | 14 | 40 | 39.3 | 0.9825 | 7 | Completed
PRJ-H-202 | Software/Migration | 1 | 14 | 40 | 36.2 | 0.905 | 6 | Completed
PRJ-H-202 | Software/Migration | 2 | 14 | 40 | 37 | 0.925 | 6 | Completed
PRJ-H-202 | Software/Migration | 3 | 14 | 40 | 35.2 | 0.88 | 6 | Completed
PRJ-H-202 | Software/Migration | 4 | 14 | 40 | 36.3 | 0.9075 | 6 | Completed
PRJ-H-202 | Software/Migration | 5 | 14 | 40 | 34.8 | 0.87 | 6 | Completed
PRJ-H-203 | Software | 1 | 14 | 40 | 38.2 | 0.955 | 10 | Completed
PRJ-H-203 | Software | 2 | 14 | 40 | 35.1 | 0.8775 | 10 | Completed
PRJ-H-203 | Software | 3 | 14 | 40 | 34.4 | 0.86 | 10 | Completed
PRJ-H-203 | Software | 4 | 14 | 40 | 38.2 | 0.955 | 10 | Completed
PRJ-H-203 | Software | 5 | 14 | 40 | 36.9 | 0.9225 | 10 | Completed
PRJ-H-204 | Data | 1 | 14 | 40 | 37.8 | 0.945 | 4 | Completed
PRJ-H-204 | Data | 2 | 14 | 40 | 34.6 | 0.865 | 4 | Completed
PRJ-H-204 | Data | 3 | 14 | 40 | 34.6 | 0.865 | 4 | Completed
PRJ-H-204 | Data | 4 | 14 | 40 | 34.3 | 0.8575 | 4 | Completed
PRJ-H-204 | Data | 5 | 14 | 40 | 37.4 | 0.935 | 4 | Completed
PRJ-H-205 | Software | 1 | 14 | 40 | 38.6 | 0.965 | 6 | Completed
PRJ-H-205 | Software | 2 | 14 | 40 | 39.2 | 0.98 | 6 | Completed
PRJ-H-205 | Software | 3 | 14 | 40 | 36 | 0.9 | 6 | Completed
PRJ-H-205 | Software | 4 | 14 | 40 | 37.4 | 0.935 | 6 | Completed
PRJ-H-205 | Software | 5 | 14 | 40 | 39.6 | 0.99 | 6 | Completed
PRJ-H-206 | Integration | 1 | 14 | 40 | 35.8 | 0.895 | 4 | Completed
PRJ-H-206 | Integration | 2 | 14 | 40 | 35.6 | 0.89 | 4 | Completed
PRJ-H-206 | Integration | 3 | 14 | 40 | 35 | 0.875 | 4 | Completed
PRJ-H-206 | Integration | 4 | 14 | 40 | 34.8 | 0.87 | 4 | Completed
PRJ-H-206 | Integration | 5 | 14 | 40 | 36.4 | 0.91 | 4 | Completed

## DS05_Historical_Projects
Historical_project_id | Project_type | Team_size | Duration_days | Planned_duration_days | Total_effort_days | Total_budget_scaled | Avg_velocity_ratio | Risk_count | Key_risks | PMO_standard_ver | Final_outcome | Is_outlier
PRJ-H-101 | Software/Migration | 8 | 240 | 225 | 180 | 8.6 | 0.92 | 5 | Legacy data migration; cutover risk | 2.1 | On Time | FALSE
PRJ-H-102 | Software/Migration | 7 | 210 | 210 | 155 | 7.4 | 0.95 | 4 | Vendor API delay; scope creep | 2.1 | On Time | FALSE
PRJ-H-103 | AI/ML Platform | 9 | 270 | 255 | 400 | 14.2 | 0.9 | 6 | Data quality; model drift | 2.2 | On Time | FALSE
PRJ-H-104 | AI/ML Platform | 8 | 255 | 240 | 380 | 13.1 | 0.93 | 5 | Forecast accuracy; GPU capacity | 2.2 | On Time | FALSE
PRJ-H-105 | Software | 5 | 120 | 120 | 88 | 4 | 0.94 | 3 | Integration dependency | 2.0 | On Time | FALSE
PRJ-H-199 | AI/ML Platform | 2 | 15 | 14 | 15 | 0.6 | 1 | 0 | POC only — not representative | 2.2 | Completed | TRUE
PRJ-H-201 | Software/Migration | 7 | 210 | 210 | 165.3 | 4.1 | 0.953 | 2 | Standard delivery risks | 2.1 | On Time | FALSE
PRJ-H-202 | Software/Migration | 6 | 150 | 150 | 119.4 | 3 | 0.892 | 3 | Standard delivery risks | 2.1 | Delayed | FALSE
PRJ-H-203 | Software | 10 | 240 | 210 | 172.4 | 4.3 | 0.907 | 3 | Standard delivery risks | 2.1 | Delayed | FALSE
PRJ-H-204 | Data | 4 | 150 | 150 | 143.7 | 3.6 | 0.9 | 6 | Standard delivery risks | 2.1 | Delayed | FALSE
PRJ-H-205 | Software | 6 | 120 | 105 | 82.9 | 2.1 | 0.945 | 3 | Standard delivery risks | 2.1 | On Time | FALSE
PRJ-H-206 | Integration | 4 | 240 | 225 | 246.4 | 6.2 | 0.89 | 3 | Standard delivery risks | 2.1 | On Time | FALSE

## DS06_Plan_Section_Check
Check_ID | Plan_ID | Component_ID | Custom_name | Status | Note
CHK-001 | PLAN-001 | COMP-001 |  | Complete
CHK-002 | PLAN-001 | COMP-002 |  | Complete
CHK-003 | PLAN-001 | COMP-003 |  | Complete
CHK-004 | PLAN-001 | COMP-004 |  | Complete
CHK-005 | PLAN-001 | COMP-005 |  | Complete
CHK-006 | PLAN-001 | COMP-006 |  | Complete
CHK-007 | PLAN-001 | COMP-007 |  | Complete
CHK-008 | PLAN-001 | COMP-008 |  | Complete
CHK-009 | PLAN-002 | COMP-001 |  | Complete
CHK-010 | PLAN-002 | COMP-002 |  | Complete
CHK-011 | PLAN-002 | COMP-003 |  | Complete
CHK-012 | PLAN-002 | COMP-004 |  | Complete
CHK-013 | PLAN-002 | COMP-005 |  | Weak | Present but thin — missing detailed role x allocation table
CHK-014 | PLAN-002 | COMP-006 |  | Complete
CHK-015 | PLAN-002 | COMP-007 |  | Missing | Risk Register entirely absent — Risk pillar defaults to Red
CHK-016 | PLAN-002 | COMP-008 |  | Weak | Acceptance criteria not measurable
CHK-017 | PLAN-002 |  | EVM_Cost_Tracking | Custom | PM's own section -> flag for PMO review, NOT a gap
CHK-018 | PLAN-101 | COMP-001 |  | Complete
CHK-019 | PLAN-101 | COMP-002 |  | Complete
CHK-020 | PLAN-101 | COMP-003 |  | Complete
CHK-021 | PLAN-101 | COMP-004 |  | Complete
CHK-022 | PLAN-101 | COMP-005 |  | Complete
CHK-023 | PLAN-101 | COMP-006 |  | Complete
CHK-024 | PLAN-101 | COMP-007 |  | Complete
CHK-025 | PLAN-101 | COMP-008 |  | Complete
CHK-026 | PLAN-102 | COMP-001 |  | Complete
CHK-027 | PLAN-102 | COMP-002 |  | Complete
CHK-028 | PLAN-102 | COMP-003 |  | Complete
CHK-029 | PLAN-102 | COMP-004 |  | Complete
CHK-030 | PLAN-102 | COMP-005 |  | Complete
CHK-031 | PLAN-102 | COMP-006 |  | Complete
CHK-032 | PLAN-102 | COMP-007 |  | Complete
CHK-033 | PLAN-102 | COMP-008 |  | Complete
CHK-034 | PLAN-103 | COMP-001 |  | Complete
CHK-035 | PLAN-103 | COMP-002 |  | Complete
CHK-036 | PLAN-103 | COMP-003 |  | Complete
CHK-037 | PLAN-103 | COMP-004 |  | Complete
CHK-038 | PLAN-103 | COMP-005 |  | Complete
CHK-039 | PLAN-103 | COMP-006 |  | Complete
CHK-040 | PLAN-103 | COMP-007 |  | Complete
CHK-041 | PLAN-103 | COMP-008 |  | Complete
CHK-042 | PLAN-104 | COMP-001 |  | Complete
CHK-043 | PLAN-104 | COMP-002 |  | Complete
CHK-044 | PLAN-104 | COMP-003 |  | Complete
CHK-045 | PLAN-104 | COMP-004 |  | Complete
CHK-046 | PLAN-104 | COMP-005 |  | Complete
CHK-047 | PLAN-104 | COMP-006 |  | Complete
CHK-048 | PLAN-104 | COMP-007 |  | Complete
CHK-049 | PLAN-104 | COMP-008 |  | Complete

## DS07_Project_Plan_Summary
Plan_ID | Project_ID | Project_name | Plan_set | Effort_MD | Duration_months | Velocity_MD_month | Team_size | Risk_count | Top_risk_score | THI_pct | Peak_role_busy_rate_pct | On_time_history_pct | Feasibility_status
PLAN-001 | PRJ-001 | Project Orion (Core Banking) | To_Review | 168 | 7 | 24 | 16 | 5 | 20 | 18 | 95 | 92 | Feasible (Green)
PLAN-002 | PRJ-002 | Energent AI (Data Platform) | To_Review | 426 | 9 | 47.3 | 10 | 0 |  | 9 | 135 | 90 | Not feasible (Red): missing Risk Register; capacity gap (peak busy ~135%); THI 9% (<10%); weak Resource/Acceptance
PLAN-101 | PRJ-101 | Project Apollo | To_Review | 157.5 | 7 | 22.5 | 6 | 6 | 8 | 18.9 | 103 | 94 | Feasible (Green)
PLAN-102 | PRJ-102 | Project Vega | To_Review | 180 | 8 | 22.5 | 8 | 4 | 10 | 21.8 | 108 | 89 | Feasible (Green)
PLAN-103 | PRJ-103 | Project Lyra | To_Review | 180 | 8 | 22.5 | 8 | 6 | 13 | 21.2 | 89 | 91 | Feasible (Green)
PLAN-104 | PRJ-104 | Project Draco | To_Review | 140 | 5 | 28 | 12 | 4 | 13 | 17.9 | 96 | 93 | Feasible (Green)

## DS08_Role_Capacity
Capacity_ID | Role | Headcount | Capacity_MD_month | Busy_rate_pct | Available_MD_month | Note
CAP-01 | Backend Developer | 8 | 176 | 92 | 14 | Near full
CAP-02 | Data Engineer | 5 | 110 | 78 | 24 | Some headroom
CAP-03 | ML Engineer | 4 | 88 | 85 | 13 | Fairly busy (many M2 tasks)
CAP-04 | DevOps | 3 | 66 | 70 | 20 | OK
CAP-05 | Frontend Developer | 4 | 88 | 60 | 35 | Good headroom (recent hires)
CAP-06 | QA Engineer | 4 | 88 | 75 | 22 | OK
CAP-07 | UX/UI Designer | 3 | 66 | 65 | 23 | OK
CAP-08 | Security Engineer | 2 | 44 | 95 | 2 | Bottleneck — PCI/audit
CAP-09 | Business Analyst | 2 | 44 | 55 | 20 | Good headroom
CAP-10 | Project Manager | 3 | 66 | 80 | 13 | OK

## REF_Member_Master
Shared master — identical rows appear in PMO_02 file.
Member_ID | Full_name | Role_title | Department | Employment | Std_hours_week
EMP-001 | Nguyen Van An | Backend Developer | Backend | FT | 40
EMP-002 | Tran Thi Bich | Data Engineer | Data | FT | 40
EMP-003 | Le Van Cuong | ML Engineer | AI/ML | FT | 40
EMP-004 | Pham Thi Dung | Backend Lead | Backend | FT | 40
EMP-005 | Hoang Van Em | DevOps Engineer | Platform | FT | 40
EMP-006 | Do Van Khoa | Security Engineer | Security | FT | 40
EMP-007 | Bui Thi Hoa | UX/UI Designer | Design | PT | 20
EMP-008 | Ngo Thi Lan | Business Analyst | BA | FT | 40
EMP-009 | Ly Van Minh | Frontend Developer | Frontend | FT | 40
EMP-010 | Truong Thi Nga | QA Engineer | QA | FT | 40
EMP-011 | Vu Thi Mai | Engineering Manager | Engineering | FT | 40
EMP-012 | Dang Van Phuc | PMO Lead / PM | PMO | FT | 40
EMP-101 | Le Anh Tuan | Project Manager | PMO | FT | 40
EMP-102 | Dao Chi Nam | Project Manager | PMO | FT | 40
EMP-103 | Hoang Hieu Nam | Backend Developer | Backend | FT | 40
EMP-104 | Do My Quan | Business Analyst | BA | FT | 40
EMP-105 | Do Trang Binh | DevOps Engineer | Platform | FT | 40
EMP-106 | Do Yen Quynh | Frontend Developer | Frontend | FT | 40
EMP-107 | Ho Hung Thao | Data Engineer | Data | FT | 40
EMP-108 | Phan Nhung My | Frontend Developer | Frontend | FT | 40
EMP-109 | Phan Ha Ha | DevOps Engineer | Platform | FT | 40
EMP-110 | Pham Trang Anh | Frontend Developer | Frontend | FT | 40
EMP-111 | Do Anh Hieu | Business Analyst | BA | FT | 40
EMP-112 | Ngo Tuan Hieu | Business Analyst | BA | FT | 40
EMP-113 | Pham Ha Viet | Backend Developer | Backend | PT | 20
EMP-114 | Tran Long Giang | UX/UI Designer | Design | PT | 20
EMP-115 | Cao Nam Long | UX/UI Designer | Design | FT | 40
EMP-116 | Cao Ngan Thao | QA Engineer | QA | FT | 40
EMP-117 | Duong Dat Chi | ML Engineer | AI/ML | FT | 40
EMP-118 | Duong Nhung Binh | UX/UI Designer | Design | FT | 40

## REF_Project_Master
Shared master — identical rows appear in PMO_02 file.
Project_ID | Project_name | Project_type | Status | Is_historical
PRJ-001 | Project Orion (Core Banking) | Software/Migration | Active | FALSE
PRJ-002 | Energent AI (Data Platform) | AI/ML Platform | Active | FALSE
PRJ-003 | Project Titan (Internal Tools) | Software | Active | FALSE
PRJ-H-101 | Mercury Core Migration | Software/Migration | Completed | TRUE
PRJ-H-102 | Saturn Banking Upgrade | Software/Migration | Completed | TRUE
PRJ-H-103 | Comet ML Pipeline | AI/ML Platform | Completed | TRUE
PRJ-H-104 | Nebula Forecast Engine | AI/ML Platform | Completed | TRUE
PRJ-H-105 | Pulsar CRM | Software | Completed | TRUE
PRJ-H-199 | Flux POC | AI/ML Platform | Completed | TRUE
PRJ-101 | Project Apollo | Software/Migration | Active | FALSE
PRJ-102 | Project Vega | Software | Active | FALSE
PRJ-103 | Project Lyra | Software/Migration | Active | FALSE
PRJ-104 | Project Draco | Integration | Active | FALSE
PRJ-105 | Project Orbit | Integration | Active | FALSE
PRJ-106 | Project Helios | Software/Migration | Active | FALSE
PRJ-107 | Project Atlas | Mobile | Active | FALSE
PRJ-108 | Project Zephyr | Data | Active | FALSE
PRJ-H-201 | Project Zephyr (archived) | Software/Migration | Completed | TRUE
PRJ-H-202 | Project Cobalt (archived) | Software/Migration | Completed | TRUE
PRJ-H-203 | Project Quartz (archived) | Software | Completed | TRUE
PRJ-H-204 | Project Nimbus (archived) | Data | Completed | TRUE
PRJ-H-205 | Project Cedar (archived) | Software | Completed | TRUE
PRJ-H-206 | Project Falcon (archived) | Integration | Completed | TRUE

## REF_KPI_Norms
Norm_ID | Metric | Formula | Green | Yellow | Red | Used_for
N01 | Busy Rate | Planned_h / Available_h | 85-110% | 111-119% | >120% or <75% | Overbook/Idle — Problem 2 + feasibility Problem 1
N02 | Utilization Rate | Worked_h / Available_h | 75-90% | 60-74% / 91-100% | <60% or >100% | Real intensity; >100% burnout — Problem 2
N03 | Billable Rate | Billable_h / Worked_h | >=80% | 70-79% | <70% | Revenue-generating hours — Problem 2
N04 | Bench Rate | Bench_h / Available_h | <=10% | 11-20% | >20% | Unassigned capacity — Problem 2 (idle)
N05 | Overtime Ratio | OT_h / Standard_h | <=5% | 6-15% | >15% | Leading burnout — Problem 2 (OT edge)
N06 | Effort Consumption | Actual_h / Planned_h | 85-110% | 75-84% / 111-119% | <=75% or >=120% | RA vs Timesheet mismatch — Problem 2 + Problem 1
N07 | On-time Delivery | On-time_MS / Total_MS | >=90% | 70-89% | <70% | Benchmark feasibility — Problem 1
N08 | SPI | EV / PV | 0.95-1.05 | 0.85-0.94 / 1.06-1.15 | <0.85 or >1.15 | Schedule realism — Problem 1
N09 | Velocity Variance | StdDev(5 sprint)/Avg | <=15% | 16-25% | >25% | Forecast reliability — Problem 1
N10 | THI | Non-dev_h / Total_h | 15-25% | 10-14% / 26-35% | <10% or >35% | Tech-debt prevention budget — Problem 1
N11 | Risk Closure Rate | Risks_closed / Total | >=80% | 60-79% | <60% | Whether RAID is alive — Problem 1
N12 | Training Compliance | Done / Required | 100% | 85-99% | <85% | Valid edge case (training) — Problem 2

## Answer_Key
Grading key — remove before distributing to the team if running a blind contest.
Finding_ID | Problem | Entity_type | Entity_id | Issue_type | Expected_detection | Severity
F-01 | Problem 1 | Plan | PLAN-002 | Missing_section | Risk Register (S07) missing -> Risk pillar defaults to Red | High
F-02 | Problem 1 | Plan | PLAN-002 | Weak_section | Resource_Plan & Acceptance_Criteria are thin | Medium
F-03 | Problem 1 | Plan | PLAN-002 | Feasibility | Peak role busy ~135% + THI 9% (<10%) | High
F-04 | Problem 1 | Plan | PLAN-002 | Custom_section | EVM_Cost_Tracking is custom -> flag for review, NOT a gap | Info
F-05 | Problem 1 | Plan | PLAN-001 | Baseline_OK | All 8 sections present; velocity 24 matches Migration benchmark ~22.5 -> feasible | Info
F-06 | Problem 1 | Benchmark | PRJ-H-199 | Benchmark_outlier | Exclude from benchmark (15 MD/0.5mo, too small) | Info
F-1C | Problem 1 | Plan | PLAN-002 | Dependency_cycle | Cycle TASK-E07<->TASK-E08 + test-before-build (E06) | High